## MigrationAuditSheet
Old URL | New URL | Page Title | Content Match | Issue Type | Description | Priority | Screenshot Link | Status | Recommendation
/home | /home | Homepage | Partial | Layout Issue | Hero section text alignment differs from old site, affecting readability | Medium | Google Drive Link link/ss1 | Closed | Adjust alignment to match original design
/about | /about-us | About Us | No | Missing Content | One full paragraph from old site is missing in new site | High | Google Drive Link link/ss2 | Fixed | Add missing paragraph from old version
/contact | /contact-us | Contact Page | No | Form Issue | Contact form not present in new site | High | Google Drive Link link/ss3 | Fixed | Re-add contact form and validate submission
/services | /services | Services | Yes | - | Content matches correctly | Low | Google Drive Link link/ss4 | Open | No action required
/blog | /blog | Blog Page | Partial | Broken Link | 2 blog links redirect to 404 page | High | Google Drive Link link/ss5 | Fixed | Fix broken links or update URLs
/pricing | /pricing | Pricing Page | Partial | SEO Issue | Meta description missing in new site | Medium | Google Drive Link link/ss6 | ReTest | Add meta description for SEO
/faq | /faq | FAQ Page | No | Content Missing | 3 FAQ questions missing compared to old site | Medium | Google Drive Link link/ss7 | Closed | Add missing FAQs
/gallery | /gallery | Gallery | Partial | Image Issue | Images not loading on mobile view | High | Google Drive Link link/ss8 | Closed | Fix image responsiveness
/testimonials | /reviews | Testimonials | No | Content Missing | Testimonials section not migrated | High | Google Drive Link link/ss9 | Closed | Re-add testimonials content
/signup | /register | Signup Page | Partial | Button Issue | “Submit” button not clickable | High | Google Drive Link link/ss10 | Closed | Fix button action