## Summary
| Overall progress of the QA cycle(Ontime, delayed, Stopped) | On time
| Total number of test cases | 27
| Test cycle duration | 5 days
Status for
| Number of test cases planned | 6
| Number of test cases executed | 5
| Number of test cases executed overall | 21
| Number of defects encountered today | 1
| Number of defect encountered so far | 4
| Number of critical defects- still open | 1
Overall status
| Number of test cases planned | 27
| Number of test cases executed | 21
| Number of passed test cases | 17
| Number of Fail test cases | 4
| Pass Percentage of the defects | 81%
| Defects density | 0.19
| Critical defects percentage | 25%

## Detailed status
Module | Scenarios | Total | Pass | Date of Execution(Can be past, present or future date) | Status(Pass/Fail/blocked/not executed) | Defect ID- Brief description | Severity | Status
Login | Valid Login | 5 | 5 | 2024-08-31 | Pass
Registration | Invalid email | 4 | 4 | 2024-08-31 | Pass
Search | Product Search | 6 | 6 | 2024-08-31 | Pass
Cart | Remove Item | 4 | 3 | 2024-08-31 | Fail | 1028: All cart items disappear when removing last item after selecting even number of products | 1- High | Open
Checkout | Payment flow | 8 | 8 | 2024-08-31 | Pass

## Bug report
Defect ID | Defect Description | Environment | Module | Steps to reproduce | Severity | State | Impact | Created by | Assigned to
1028 | All cart items disappear when removing last item after selecting even number of products | Chrome, Windows 11 | Cart | 1. Login to the application 2. Add even number of products to cart (example: 2 or 4 items) 3. Navigate to cart page 4. Remove the last item from the cart Expected result: Only the selected item should be removed from the cart. Remaining items should still be visible. Actual Result: When an even number of items are added to the cart and the last item is removed, all remaining items are also removed unexpectedly. The cart becomes empty. | 1- High | Open | User loses all selected cart items unexpectedly, leading to poor user experience. | Nilava | Dev representative